## Slide 1: Behavioral Wellness Program for Public Safety Forces

## Slide 2: Project Timeline
Sep. 2020
Identification of behavioral wellness project with police officers.
Initiation of literature review by COR
Oct. 2020
Project approved by CFBH Board
Identification of ACPD as project site
Nov. 2020
Completion of literature review
Meetings with ACPD
Dec. 2020
ACPD willing to serve as demonstration site
COR to conduct needs assessment
Jan. 2021
COR interviews with ACPD
Ongoing conversations with ACPD and potential partners
Feb. 2021
COR completes design of Needs Assessment Survey
Meetings with ACPD to outline MOU

## Slide 3: Program Plan

## Slide 4: Plan dates
Mar. 2021
Complete project approvals
Launch Needs Assessment
Apr. 2021
Complete Needs Assessment and report
Identify behavioral wellness program objectives
Identify program components
Identify measurable indicators of behavioral wellness
May 2021
Create initial program evaluation tool
Launch behavioral wellness program

## Slide 5: Program Completion
Nov. 2021
First follow-up evaluation
May 2022
Final evaluation and report